## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to Project (Form Filling AI) | MUST HAVE | No dependency | Harini P | 3- Completed
S2 | S2 | US-001 | Workflow Creation and Project Goal Document | MUST HAVE | Lucid Chart | Harini P | 3- Completed
S3 | S3 | US-001 | Document Discussion (Agile Template, Defect Tracker, Unit Testing) | MUST HAVE | No Dependency | Harini P | 3- Completed
S4 | S4 | US-001 | Use Case Research and Preparation | MUST HAVE | Browser | Harini P | 3- Completed
S5 | S5 | US-001 | Python Practice Kit Completion | MUST HAVE | Coding Planform(Hackerank) | Harini P | 3- Completed
S6 | S6 | US-001 | SQL Practice Kit Completion | MUST HAVE | Coding Planform(Hackerank) | Harini P | 3- Completed
S7 | S7 | US-001 | Python Skill certificate from Hackerrank | MUST HAVE | Coding Planform(Hackerank) | Harini P | 3- Completed
S8 | S8 | US-001 | SQL Skill certification from Hackerrank | MUST HAVE | Coding Planform(Hackerank) | Harini P | 3- Completed
S9 | S9 | US-001 | Discussion on OPPS concepts, List, Tuples, Set, Dictionary - also, prepared document covering all these topics | MUST HAVE | No Dependency | Harini P | 3- Completed
S10 | S10 | US-001 | Discussion on Lamda Functions, Loops- also, prepared document covering all these topics | MUST HAVE | No Dependency | Harini P | 3- Completed
S11 | S11 | US-001 | Discusion on Flask, also prepared document covering important topics of flask | MUST HAVE | No Dependency | Harini P | 3- Completed
S12 | S12 | US-001 | Project discussion- Front end part of the project is demonstrated as a team | MUST HAVE | VS code, Environment dependencies, | Harini P | 3- Completed
S13 | S13 | US-001 | Project discussion- Model building part of the project is demonstrated as a team (Team -Group 2) | MUST HAVE | VS code, Environment dependencies,Open AI API | Harini P | 3- Completed
S14 | S14 | US-001 | Discussion on SQL basics - Topics covered: Joins, Where and Having Clause, Aggregation | MUST HAVE | No Dependency | Harini P | 3- Completed
S15 | S15 | US-001 | Project discussion - Integration of the model with front- end and connecting it with database | MUST HAVE | VS code, Environment dependencies,Open AI API , | Harini P | 3- Completed
S16 | S16 | US-001 | Accuracy improvement for capturing the audio by filtering it out from background noise | MUST HAVE | VS code, Environment dependencies,Open AI whisper model , Mysql | Harini P | 3- Completed
S17 | S17 | US-001 | Databse integration - Using mysql, the data is retrieved and stored in the database | SHOULD HAVE | VS code, Environment dependencies,Open AI whisper model , Mysql | Harini P | 3- Completed
S18 | S18 | US-001 | Deployment part - Deployed the website using the Railway platform without database | SHOULD HAVE | Git hub repo, Railway Account | Harini P | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 28 | 15 | 11 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T-001 | Research speech-to-text tools | 2024-11-15 | 2024-11-16 | Harini P | Others | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-002 | Develop noise cancellation module | 2024-11-17 | 2024-11-20 | Harini P | Build | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-003 | UI DEVELOPMENT | 2024-11-21 | 2024-11-22 | Harini P | Design | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-004 | Integrate speech-to-text with the form UI | 2024-11-23 | 2024-11-25 | Harini P | Coding | 3- Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-005 | Test form-filling accuracy with data | 2024-11-27 | 2024-11-28 | Harini P | System Test | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-006 | Deployment | 2024-12-22 | 2024-12-23 | Harini P | Others | 3- Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Difficulty identifying the best speech-to-text API | Researched and compared APIs (Google Speech-to-Text, Whisper AI, Azure Speech). Finalized Whisper AI.
Sprint 2 | Day 7 | Noise cancellation module is introducing lag in processing | Optimized code by using faster libraries like PyDub and reducing unnecessary pre-processing steps.
Sprint 3 | Day 14 | Integration with the form UI is causing input delays. | Debugged the UI code and optimized the asynchronous functions for real-time updates.
Sprint 4 | Day 21 | Accuracy of recognition is below 80%. | Woked in improving the accuracy
Sprint 5 | Day 35 | API rate limits during testing with large datasets. | Implemented batch testing and optimized API requests to stay within limits.
Sprint 6 | Day 42 | Testing environment not simulating real-world noise conditions. | Added real-world noise samples to the test environment to improve robustness.
Sprint 7 | Day 49 | Minor issues in storing data into database Mysql | Debugged the data storing query and connectivity to rsolve the issue.
Sprint 8 | Day 56 | Deployment issue- Finding difficult to deploy the project using free hosting websites | Foud Railway website for deploying the project without database

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 21/12/124 | 2024-12-27 | Harini , Rishiraj,Nandini , Vaishnavi | Prioritizing tasks based on urgency and impact. | Overloading daily task efforts. | Regular progress tracking and updates. | Created a task prioritization matrix and allocated time effectively for critical tasks.
2 | Sprint 2 | 2024-12-01 | 2024-12-05 | Harini, Rishiraj | Testing the form-filling model in noisy environments. | Ignoring small bugs during testing. | Optimizing the model for medical terms. | Conducted real-world noise testing and fixed minor bugs in the module to ensure smooth functionality.
3 | Sprint 3 | 2024-12-06 | 2024-12-07 | Harini | Automating repetitive testing tasks. | Delaying documentation | Ensuring form UI integration is user-friendly. | Wrote test scripts to automate repetitive tests and started preparing documentation for smoother handoffs.
3 | Sprint 4 | 2024-12-22 | 2024-12-23 | Harini , Nandini , Vaishnavi | Deployment part | Issues in finding free website for deployment | Research on deploymen part | Found railway platform and deployed the project without database